## SPRINT-2-Provisional-Plan
Sprint-2 Backlog
Post Configuration - Viewer Actions - Save / Comment / Report - Frontend, API , Integration
Adding Friends - API / Backend
Bugs Reported for Authentication feature
Sprint Provisional Plan
Task type | Task | Sub Task | Responsible | Start Date | End Date | Priority
Requirement Gathering | Discuss Client requirements for : 1. POST Actions - Save 2. POST Actions - Comment 3. POST Actions - Report 4. Adding Friends | Setup meeting with client. | Srishti | 2021-02-22 | 2021-02-23 | High
|  | Prepare Questionare for actions for client | Team | 2021-02-22 | 2021-02-23 | High
Requirement Analysis | Confirm Client requirements for : 1. POST Actions - Save 2. POST Actions - Comment 3. POST Actions - Report 4. Adding Friends | Analyze last meetings inputs and prepare new questionare if required | Margaret + Srishti | 2021-02-24 | 2021-02-25 | High
|  | Setup meeting with client. | Srishti | 2021-02-24 | 2021-02-25 | High
Specifications | Specify functional details for | Adding friends | Srishti + Kanav | 2021-02-25 | 2021-02-26 | High
|  | POST Action - Save | Srishti + Sanju Atwal
POST Action - Comment
POST Action - Report
| Specify user interface | POST Action - Save | Srishti + Sidhartha
POST Action - Comment
|  | POST Action - Report |  | 2021-02-25 | 2021-02-27
| Specify what needs to be stored in DB | POST Action - Save | Srishti + Sanju Atwal | 2021-02-25 | 2021-02-26
POST Action - Comment
POST Action - Report
|  | Adding friends | Srishti + Kanav
| Update srs |  | Srishti | 2021-02-26 | 2021-02-27 | Low
Design | Define DB schema |  | Srishti | 2021-02-27 | 2021-02-28 | High
| Define flow for each action. | POST Action - Save |  | 2021-02-26 | 2021-03-01
POST Action - Comment
POST Action - Report
Adding friends
| Update design document |  |  | 2021-02-27 | 2021-03-02 | Low
Development | POST Actions - Frontend | HTML & CSS / Saas | Sidhartha | 2021-02-25 | 2021-03-03 | High
|  | API Integration | Sidhartha & Sanju | 2021-03-03 | 2021-03-05
| POST Actions - API / Backend | Save | Sanju | 2021-02-25 | 2021-02-27 | High
|  | Comment |  | 2021-02-27 | 2021-02-28
|  | Report |  | 2021-03-01 | 2021-03-03
| Add Friends - API / Backend |  | Kanav | 2021-02-25 | 2021-03-05 | High
| Bugs reported for Authentication |  | Sidhartha / Srishti | 2021-02-22 | 2021-02-24 | Medium
Testing | Test Post Configuration - Add/ Update |  | Margaret | 2021-02-22 | 2021-03-01 | High
| Write Test cases | Post Configuration - Viewer Actions - Save | Margaret | 2021-03-02 | 2021-03-03 | Medium
|  | Post Configuration - Viewer Actions - Comment | Margaret | 2021-03-03 | 2021-03-04
|  | Post Configuration - Viewer Actions - Report | Margaret | 2021-03-04 | 2021-03-05
|  | Adding friends | Margaret | 2021-03-01 | 2021-03-02 | High
Deployment | AWS |  | Sidhartha + Kanav | 2021-02-22 | 2021-02-25 | Low

## SPRINT-2-Effective-Plan
Sprint Effective Plan
Task type | Task | Sub Task | Responsible | Time Spent |  | Artifact
Requirement Gathering | Discuss Client requirements for : 1. POST Actions - Save 2. POST Actions - Comment 3. POST Actions - Report 4. Adding Friends | Decide questions to ask and confirm queries | Margaret Kanav Sanju Sidhartha | 1 hr | 2021-02-23 | Confirm Moderation feature expectation from client end Share current plan for all the planned features and ask for feedback
|  | Meeting with the customer | Kanav Sanju Sidhartha | 55 min | 2021-02-23 | Feedback- Closed Points: 1. POST Actions- Save & Comment. 2. Adding friends Open Points: 1. UI for moderation feature (POST Actions - Report)
Requirement Analysis | Confirm Client requirements for : 1. POST Actions - Save 2. POST Actions - Comment 3. POST Actions - Report 4. Adding Friends | Analyze last meetings inputs | Srishti + Kanav | 1 hr | 2021-02-25 | Adding a UI for moderation feature with the current development team would not be possible, we would require more resources i.e. another engineer; development cost & time will be impacted as well due to onboarding and training required to develop and integrate the required feature. Given the time and resource constraints, keeping the moderation feature limited to backend for the initial product release. If we decide to move ahead and continue the project after first release in April, we can plan on adding the feature to incremental releases depending on how we continue the contract for building the software.
|  | Meeting with the customer | Srishti | 5 min | 2021-02-26 | Meeting was cancelled due to inavailability of both client and multiple team members. Open discussion for "POST Actions - Report" was closed with client over chat ( Teams ). Final Decision - Feature will be implemented at backend level only for the first release.
Specifications | Specify functional details for | Adding friends | Srishti + Kanav | 2 hr | 2021-02-25 | To do : •A user can send friend request to a person to add them to their friend list for keeping an update of their stories and experiences while sharing his own with them. •In case, User A adds no friend, application will act as a private journal for user A. Other users will be able to find posts of user A only if they are marked public. •A user can only add people already registered on application as friends. To be added in future: •Option to migrate connection list from Facebook/Google
|  | POST Action - Save | Srishti | 15 min | 2021-02-25 | •Every viewable post will also be saveable, for future reference or read. •Every post saved shall be accessible from “Reading List” grid on dashboard.
|  | POST Action - Comment |  | 15 min | 2021-02-25 | •User can add comment to a post. •Add a comment text box shall be available for user to add a comment on post. •Recent 3 comments shall only be visible when reading a post.
|  | POST Action - Report |  | 15 min | 2021-02-26 | •User-Only Moderation feature – will rely on users to filter out inappropriate and irrelevant content. •User shall be able to mark a post as spam/abusive. •Application shall automatically hide the post if it is reported several times.
| Specify user interface | POST Action - Save | Srishti | 30 min | 2021-02-26 | Buttons for all three actions will be added for each viewable post. When reading a post, user will have option to click on any 3 actions to be performed.
POST Action - Comment
POST Action - Report
| Specify what needs to be stored in DB | POST Action - Save |  | 15 min | 2021-02-26 | Post Id will be added to Saved Posts list in the object for the specific user in MongoDB
|  | POST Action - Comment |  | 20 min | 2021-02-27 | Comment & document id for user who commented will be stored in Comments list in Post object for which comment was added.
|  | POST Action - Report |  | 20 min | 2021-02-27 | A flag and counter will be maintained in every Post object in Posts Collection. If and when a post is reported, counter will be incremented and flag will be marked true.
|  | Adding friends |  | 20 min | 2021-02-27 | A Friends set will be stored in User specific object in Users collection. This friend set shall contain unique user document ids for the friends.
| Update srs |  |  | 3 hrs | 01-03-2021 to 03-03-2021 | SRS Updated
Design | Define DB schema |  | Kanav + Sanju + Srishti | 2 hrs | 2021-02-27 | The schema for last sprint works here too. The fields to add will be listed in design.
| Define flow for each action. | POST Action - Save | Srishti + Sanju | 4 hrs | 2021-03-01 | • On click, the post will be saved for future reference. • It will be available to reader from Dashboard >> Reading List. • Post unique id will be saved to database to keep track of posts.
|  | POST Action - Comment |  |  |  | •On click, user will be allowed to enter a comment and submit it. •Comment & author will be stored in DB, in the Post specific object
|  | POST Action - Report |  |  |  | •On click, post will be marked as reported in database. •A counter will be stored to record the no. of times a post has been reported. •It will be a User-Only Moderation feature i.e., will rely on users to filter out inappropriate and irrelevant content. •A post reported by 10% of the users will be automatically hidden and considered abusive/spam. •Post author will be notified.
|  | Adding friends | Srishti + Kanav | 3 hrs | 2021-03-01 | •When the user goes to the add friends page, he will see the list of existing users in the application. •When he clicks on add friend, a request is sent to the befriended user for accepting/declining the request. •When searching for friends, search string will be compared with registered users only. •Search will work for both full and partially entered data. This friend set shall contain unique user document ids for the friends. •3 APIs will be implemented, -search – to search friends -friends – to get list of friends -acceptFriendRequest – to accept a friend request and update the friend list in db.
| Update design document | Sprint 1 and Sprint 2 features | Srishti | 2 days | 04-03-2021 to 06-03-2021 | Design document updated
Development | POST Actions - Frontend | Post Reader Actions UI | Sidhartha | 6 days | 25-02-2021 to 04-03-2021 | Basic Post Actions UI is ready
| CSS styling analysis login and dashboard | Login and Dashboard | Margaret | 3 days | 04-03-2021 to 06-03-2021 | Trending post header , Login page title
| Dashboard UI Header |  | Sidhartha | 2 days | 04-03-2021 to 06-03-2021 | Header part is ready
| POST Actions - API / Backend | Save | Sanju | 2 days | 25-02-2021 to 01-03-2021 | APIs developed. A bug found which will be handled in Sprint-3
|  | Comment |  | 3 days | 01-03-2021 04-03-2021
|  | Report |  | 3 days | 04-03-2021 to 07-03-2021
| Add Friends - API / Backend |  | Kanav | 8 days | 24-02-2021 to 05-03-2021 | APIs developed
| Bugs reported for Authentication | Invalid email id accepted during signup | Sidhartha | 1 day | 2021-02-22 | Resolved
|  | Signup successful message is not displayed | Sidhartha | 1 day | 23-02-2021 to 24-02-2021
|  | Password length check missing | Srishti | 2 days | 26-02-2021 to 01-03-2021
Testing | Test automation analaysis and base framework | Testing framework design | Margaret | 2 days | 22-02-2021 to 24-02-2021 | Inprogress
| API unit test | API flow validation |  | 1 day | 2021-02-25 | Complete
| Write Test cases and retest | Logout component validation |  | 1 day | 2021-02-26 | Complete
|  | Multiple responses generated for a single request defect report and retest |  |  |  | Complete
|  | Multiple registeration for the same user doesnt throw error bug reporting and retest |  | 1 day | 2021-02-27 | Complete
| Smoke Test | Login and Dashboard |  | 0.5 day | 2021-02-28 | Complete
|  | Signup with facebook and google |  | 0.5 day | 2021-02-28
| Close resolved bugs | Password length check missing |  | 2 days | 01-03-2021 to 03-03-2021
Signup successful message is not displayed
Invalid email id accepted during signup
Sprint Evaluation
Delayed / Moved to next sprint
Development | Reason
Post Configurations - Reader End - Frontend-API Integration | Time constraint
Deployment
Confirm Password validations are not re-checked if password updated in form
Testing | Reason
Test post configuration Add/Update | Pending dependencies at dev level
Artifacts
Adding friends APIs
Post Configuration - frontend backend
Base framework for Automation testing | Extra
Smoke testing for User Authentication | Extra
Dashboard UI Header | Extra

## SPRINT-3-Provisional-Plan
Sprint-3 Backlog
Tag an inspirer
Add a post - Location tag missing ( Location should be tagged ) - Backend + Frontend
Dashboard - Trending Posts, Reading List, General Feed - Frontend + Backend + Integration
Add Friend - Frontend, Integration
Post features - Integration
Deployment
Sprint Provisional Plan
Task type | Task | Sub Task | Responsible | Start Date | End Date | Priority
Requirement Gathering | Discuss and decide requirements for: 1. Tagging a user as inspirer 2. Dashboard features - Trending List Reading List General Feed | Decide meeting agenda and queries to confirm with client | Team | 2021-03-08 | 2021-03-09 | high
|  | Setup meeting with client | Srishti | 2021-03-09 | 2021-03-10
Requirement Analysis | Confirm requirements for: 1. Tagging a user as inspirer 2. Dashboard features - Trending List Reading List General Feed | Analyze last meetings inputs and prepare new questionare if required | Team | 2021-03-10 | 2021-03-10 | high
|  | Setup meeting with client. | Srishti | 2021-03-11 | 2021-03-12
Specifications | Specify functional details | Tagging a friend as inspirer | Srishti + Sanju | 2021-03-12 | 2021-03-13
|  | Trending Posts | Srishti + Kanav
Reading List
General Feed
| Specify user interface | Tagging a friend as inspirer | Srishti + Sidhartha | 2021-03-13 | 2021-03-14
Trending Posts
Reading List
General Feed
Add friends
| Specify database entries | Tagging a friend as inspirer | Srishti + Sanju | 2021-03-12 | 2021-03-13
| Update SRS |  |  | 2021-03-12 | 2021-03-14 | Low
Design | Define flow for API | Tagging a friend as inspirer | Srishti | 2021-03-14 | 2021-03-15
Trending Posts
Reading List
General Feed
| Update DD |  |  | 2021-03-15 | 2021-03-16 | low
Development | Tagging a friend as inspirer | API | Sanju | 2021-03-14 | 2021-03-18
| Add a post - Geo Location column | API + Frontend + Integration | Sanju | 2021-03-12 | 2021-03-14
| Add Friends | Frontent + Integration | Sidhartha |  | 2021-03-17
| Post Configuration - Reader End | Integration | Sidhartha |  | 2021-03-13
| Trending Posts | API | Srishti | 2021-03-13 | 2021-03-15
|  | Integration | Srishti | 2021-03-15 | 2021-03-16
| General Feed | API | Srishti | 2021-03-16 | 2021-03-18
|  | Integration | Srishti | 2021-03-18 | 2021-03-21
| Reading List | API | Sanju | 2021-03-11 | 2021-03-12
|  | Integration | Sanju | 2021-03-10 | 2021-03-11
| Bugs from last sprint |  | Kanav/Sidhartha
Testing | Post Configuration - Reader End |  | Margaret
Post Configuration - Writer End
| Write plan | Trending Posts
General Feed
Reading List
Deployment | Application deployment |  | Kanav | 2021-03-08 | 2021-03-19 | Highest

## SPRINT-3-Effective-Plan
Sprint Effective Plan
Task type | Task | Sub Task | Responsible | Time Spent |  | Artifact
Requirement Gathering | Discuss and decide requirements for: 1. Tagging a user as inspirer 2. Dashboard features - Trending List Reading List General Feed | Decide meeting agenda and queries to ask if any | Srishti Margaret | 1 hr | 2021-03-11 | Present Tag a post, dashboard features and plan for the sprint. Ask for client feedback.
|  | Meeting with the customer | Srishti Kanav Sanju Sidhartha Margaret | 25 min | 2021-03-11 | Feedback- Closed Points: 1. Dashboard Features Open Points: 1. Inspiration cycle suggested by client for saved posts. Since, it is the main expected feature, research and development needs to be planned here. Idea suggested by client is to use a list in DB to store hierarchy.
Requirement Analysis | Discuss and decide requirements for: Inspiration History | Analyze last meetings inputs | Srishti | 3 days | 12-03-2021 to 14-03-2021 | Client's suggestion for list will break when required to work at a large scale or if to plan a hierarchy or inspiration history as graph in later stages. Possible Solutions Researched but rejected- 1. GraphLookup on Main collection- Doesn't work well with subdocuments. 2. GraphLookup on View of subdocuments - Provides only single level hierarchy which will limit applications results and will require redesign when in future graph feature will be designed. Final Proposed Solution to team - Aggregation with Lookup & recursive algorithm to get inspirers until owner is received.
Specifications | Specify functional details for | Dashboard - Trending Posts | Srishti | 3h | 14-03-2021 to 14-03-2021 | The top 6 posts shall be displayed on dashboard "Trending List" Grid. No. of saves will decide the rank of post in treding list. Constraint - Posts from friends will only be ranked
|  | Dashboard - General Feed |  |  |  | All posts from Friends shall be displayed in "General Feed" Grid. Only 5 posts shall be visible on 1 page. Posts shall be visible in descending fashion as per there publish time, i.e., recent post will be visible on top of list.
|  | Dashboard - Reading List |  |  |  | Any post saved by user shall be visible in and accessible from "Reading List" Grid.
| Specify user interface | Dashboard - Trending List | Srishti |  |  | All three lists shall be visible on frontend as per the wireframe. Trending posts will be limited to 6 entries. General feed will be limited to 5 entries. Reading list will also be limited to 5 elements per page.
Dashboard - General Feed
Dashboard - Reading List
| Specify what needs to be stored in DB | Dashboard - Trending List | Srishti |  |  | N/A
|  | Dashboard - General Feed |  |  |  | N/A
|  | Dashboard - Reading List |  |  |  | N/A
| Update srs |  | Srishti | 2 hrs | 2021-03-18 | SRS Updated
Design | Define DB schema |  | Srishti | 1 hr | 2021-03-14 | Change in Posts Schema: When a post is saved, Users { … username: saved:[{postID}] } Posts { … savedBy:[{ user : {username}, // user who saved the post Inspired : [] // friends or users who were inspired by the user }] }
| Define flow | Dashboard - General Feed | Srishti | 3 hrs | 2021-03-15 | Use mongoDB aggregate to get the desired output. For aggregation, 1. Match the logged in user's username in users collection to reach the specific user doc. 2. For the above match's output, get posts of all users in friends array in user document using mongoDb Lookup and project them as feed.
|  | Dashboard - Reading List | Sanju
| Update design document | General Feed & Reading list | Srishti | 30 min | 2021-03-18 | Design document updated
Development | Dashboard - General Feed | API | Srishti | 1 day | 2021-03-16 | Complete
| Dashboard - Reading List | API + Frontend + Integration | Sanju | 4 days | 12-03-2021 to 17-03-2021 | Complete
| POST Actions - Integration | Save | Sanju | 2 days | 18-03-2021 to 19-03-2021 | Complete
|  | Comment |  | 2 days | 20-03-2021 to 21-03-2021 | Complete
| Add Friends - Frontend + Integration |  | Sidhartha + Kanav | 10 days | 08-03-2021 to 21-03-2021 | Complete
Testing | Post Configuration - Reader End |  | Margaret | 4- days | 08-03-2021 to 12-03-2021 | Complete
| Post Configuration - Writer End |  |  | 5 days | 14-03-2021 to 21-03-2021 | Complete
| Write plan |  |  | 2 days
Sprint Evaluation
Delayed / Moved to next sprint
Development | Reason
Trending Posts - Integration + API | Time & resource constraint
General Feed - Integration
Post Action - Integration - Report
Inspiration History | Change in requirement
Artifacts
Post reader features - Save & comment
Dashboard - General Feed API & Frontend
Dashboard- Reading List
Inspiration History - Research closed

## SPRINT-4-Provisional-Plan
Sprint-4 Backlog
Trending Posts - Integration + API
General Feed - Integration
Post Action - Integration - Report
Inspiration History
Deployment
Sprint Provisional Plan
Task type | Task | Sub Task | Responsible | Start Date | End Date | Priority
Requirement Gathering | Inspiration History | Decide meeting agenda and queries to confirm with client | Team | 2021-03-22 | 2021-03-24 | high
|  | Setup meeting with client | Team | 2021-03-24 | 2021-03-25
Requirement Analysis | Confirm requirements for: 1. Tagging a user as inspirer 2. Dashboard features - Trending List Reading List General Feed | Analyze last meetings inputs and prepare new questionare if required | Team | 2021-03-25 | 2021-03-26 | high
|  | Setup meeting with client. | Team | 2021-03-27 | 2021-03-27
Specifications | Specify functional details | Inspiration History | Srishti | 2021-03-30 | 2021-03-31 | high
| Specify user interface | Inspiration History, Notification mechanism
| Specify database entries | Inspiration History
| Update SRS |  |  |  |  | Low
Design | Define flow for API | Inspiration History | Srishti + Sidhartha | 2021-04-01 | 2021-04-01 | Highest
| Update DD |  |  |  |  | low
Development | Inspiration History | API | Srishti | 2021-04-02 | 2021-04-04 | Highest
| Inspiration | Integration | Sidhartha | 2021-04-03 | 2021-04-04 | High
| General Feed | Integration | Sanju | 2021-04-22 | 2021-04-27 | High
| Post Configuration - Reader End - Report | Integration | Kanav | 2021-04-22 | 2021-04-02 | Medium
| Branding on Login and Signup |  | Margaret | 2021-04-22 | 2021-04-02 | Medium
| Bugs from last sprint |  | Team | 2021-04-22 | 2021-04-04 | MEdium
Testing | Regression Testing for complete product | Execute the automated and manual tests | Margaret | 2021-04-22 | 2021-04-04 | High
| Update test plan | Documentation | Margaret | 2021-04-22 | 2021-04-04 | Medium
| Update SQAP | Documentation | Margaret | 2021-04-22 | 2021-04-04 | High
Deployment | Application deployment |  | Kanav | 2021-04-22 | 2021-04-04 | Highest

## SPRINT-4-Effective-Plan
Sprint Effective Plan
Task type | Task | Sub Task | Responsible | Time Spent |  | Artifact
Requirement Gathering | Inspiration Cycle | Discussion with client over chat | Sidhartha | 30 min | 2021-03-25
Requirement Analysis | Discuss and decide requirements for: Inspiration History | Analyze last meetings inputs & close requirements with client ( Done over chat ) | Sidhartha | 30 min | 2021-03-26
Specifications | Specify functional details for | Inspiration History | Srishti | 3 hrs | 2021-03-27 | Api shall return inspiration cycle for a post saved by user. For eg, User A created post - 1 User B saved it. Now if user B opens the post, inspiration cycle shown will be B->A i.e. B was inspired by A User C is notified "B saved a Post" and he clicks the notification and saves the post too. Now if user C opens the post, inspiration cycle shown will be C->B->A i.e. C was inspired by B and so on. For api to work, following payload is needed : user : for which cycle is to be fetched. owner : post owner title : post title If user C is logged in, and has saved this post, he shall always see the cycle for himself.
| Specify user interface | Inspiration History | Srishti + Sidhartha | 2 hrs | 2021-03-27 | Inspiration cycle will be visible on frontend when and if an already saved post is open up by user to view.
| Specify what needs to be stored in DB | Inspiration History | Srishti | 30 min | 2021-03-27 | 1. Notification details 2. SavedBy - User & Inspirer combination
Design | Define DB schema | Inspiration History | Srishti | 1 hr | 2021-03-30 | Change in Posts Schema: When a post is saved, Users { … username: saved:[{postID}], notifications:[{ notification_type : post_saved, content : "friend's username" saved a post, notifier : "friend's username" postId : id saved by friend }] } Posts { … savedBy:[{ user : {username}, // user who saved the post Inspired : [] // friends or users who were inspired by the user }] }
| Define flow | Trending Post | Srishti | 2 hrs | 2021-04-03 | Use mongoDB aggregate to get the desired output. For aggregation, 1. Match the logged in user's username in users collection to reach the specific user doc. 2. For the above match's output, get posts of all users in friends array in user document using mongoDb Lookup and project as feed. 3. For the above feed, unwind results to get separate docs 4. Project the unwinded results as original data format and add another field count that keeps track of size of savedBy subdocument to check the no. of saves for a post. 5. Sort the above output on the basis of count field. 6. Limit output to 6
|  | Change in save post logic | Srishti | 2 hrs | 2021-03-31 | When a user clicks on save post, backend savepost API shall receive "notifier" in payload. This notifier will be used to track if a user reached the post via a notification or directly via the general feed. When user goes to a post through a notification, frontend shall add the notification sender as referer while redirecting user to the post. If save is clicked, this referer shall be loaded to notifier and sent as payload to API. API will perform 2 operations on this data : 1. Push entry of User saving a post i.e. savedBy : [{user : A, inspired : [B]}, { user : B, inspired : [] } , { user : C, inspired : [] }] 2. Push entry for "C was inspired by B" i.e. savedBy : [{user : A, inspired : [B]}, { user : B, inspired : [C] } , { user : C, inspired : [] }] In case of normal save via general feed, i.e, owner of the post acted as inspirer, notifier shall not be sent by frontend. If notifier is not valid, API should save owner as inspirer for current user. ( eg : A and B )
|  | Inspiration History | Srishti | 6 hrs | 2021-03-30 | Considering the schema design : Post1: { title: "1" owner: "A" SavedBy:[{user:"B",inspired:["C"]},{user:"A",inspired:["B"]},{user:"C",inspired:[]}] ..... } Run Mongoose's aggregate function over the posts collection. Repeat S1 and S2 until cycle completed is set to true S1 - For aggregation, 1. Match post's title and owner to get the post for which cycle is to be created. 2. Unwind the document to get savedBy subdocuments into separate docs. 3. Match "current user" with SavedBy.inspired to fetch the document where user was inspired. 4. project output to return SavedBy.user as inspirer. S2 - If return values is not null, Match the output with owner to check if end of cycle is reached. If yes, set cycle completed to true and return the cycle. If false, set current user to return value of aggregate query. else set cycle completed to true and return empty cycle.
Development | Inspiration History | Notification Mechanism | Srishti + Sidhartha | 1 day | 2021-04-01 | Complete
|  | API | Srishti | 1.5 days | 02-04-2021 to 03-04-2021
|  | Integration | Sidhartha + Srishti
| General Feed Integration | Integration | Srishti + Sidhartha | 0.5 day | 2021-03-31
| Trending Posts | API | Srishti | 1 day | 03-04-2021 to 04-04-2021
|  | Integration | Sidhartha
| Bug | 1. Saved Post not being updated in DB correctly 2. Do not display current user as option for adding friend | Srishti | 0.5 day | 2021-03-31
| Branding for Login and Signup page and User settings issue fix | 1. Added branding on login and signup 2. Display user name on settings page and remove extra fields | Margaret | 2 days | 22-03-2021 to 23-03-2021
Testing | Update the test plan | 1. Update the test scenarios based on the logic change and UI change | Margaret | 1 day | 25-03-2021 | Complete
| Retest closed defects | Retest the closed defects and validate them |  | 2 days | 26-03-2021 to 27-03-2021
| create defects and track them | Test the application and raise defects for faulty functionlaities and track them |  | 2 days | 28-03-2021 to 29-03-2021
| Test case execution manual / automation | Run the automated and manual test scripts to verify the correctness and completeness of the developed application |  | 2 days | 01-04-2021 to 02-04-2021
Deployment | To deploy the application on server |  | Sidhartha | 3 days | 22-03-2021 to 04-04-2021 | Basic setup complete
|  |  | Margaret | 2 days | 03-04-2021 to 04-04-2021 | Basic setup on Jenkins
Sprint Evaluation
Delayed / Moved to next sprint
Artifacts
Deliverable Ready with features from all 4 sprints

## Backlog
Chatbot
MFA
Role based permissions
radio buttons for abuse/spam
location rating
Security
Private policy